## Sheet1
Steps | Modules | Sub-Tasks | Planning Phase | Implementation Phase
Note: Use the sections which you feel are valid for your project.
Business & Data Understanding
| Define the Scope of the ML Application | Business Problem | Instlit's AI platform for global salary benchmarking is hindered by inconsistent job roles, missing data and varying geographical compensation standards, complicating accurate salary predictions across roles, experience, and regions. | Implemented an AI-powered salary prediction system to support HR and recruitment teams in setting competitive compensation packages for tech roles
|  | Business Objectives (maximum 4 to 5 words & to the extent possible please use terms such as Minimize & Maximize) | Maximize equitable compensation decisions | Maximize equitable compensation decisions- Maximize candidate offer acceptance. - Minimize recruitment process time.
Success Criteria
|  | Business Success Criteria | 1.Achieve 88%+ accuracy in salary predictions across roles, geographies, and experience levels. 2.Reduce data inconsistency impact to <5% error rate. 3.Enable equitable pay decisions, validated by HR stakeholders in 95%+ of test cases. | R² = 0.98212 with covering job roles, geographies, and experience levels MAPE =1.304719 achieved via preprocessing (imputation, encoding, standardization) SHAP explainability added; ~95% predictions align with HR expectations (pending full validation)
|  | ML Success Criteria | 1.Accuracy >=88% 2.Attain 95%+ stakeholder validation for equitable pay predictions using SHAP explainability. 3.Maintain model robustness with <10% performance degradation from data/model drift, monitored via MLflow and Airflow. | Achieved: - RMSE ≤ 0.243623 (Random forest: 0.243623). - R² ≥ 0.98212(Random forest: 0.98212). - MAPE ≤ 1.304719 % (Random forest:1.304719 ). - SHAP interpretability implemented (plots saved).- MAPE ≤ 3.2958% (XGBoost: 3.2958). - SHAP interpretability implemented (plots saved).
|  | Economic Success Criteria | 1.Achieve a 15% quarter-to-quarter increase in customer acquisition revenue from companies using the Instlit application. 2.Maintain customer retention rate of 95%+ to sustain revenue from existing users. 3.Reduce customer acquisition cost by 10% per quarter through optimized marketing and platform efficiency. | 1.Achieve a 15% quarter-to-quarter increase in customer acquisition revenue from companies using the Instlit application. 2.Maintain customer retention rate of 95%+ to sustain revenue from existing users. 3.Reduce customer acquisition cost by 10% per quarter through optimized marketing and platform efficiency.
Feasibility
|  | Applicability of ML technology | Supervised machine learning models, including XGBoost, Random Forest, Gradient Boosting, and Linear Regression, are effective in predicting employee compensation by analyzing key factors such as job role, location, experience, and company size. These models help generate accurate and reliable salary estimates to support fair and data-driven compensation decisions. | Supervised machine learning models, including XGBoost, Random Forest, and Linear Regression,Decision Tree are effective in predicting employee compensation.
|  | Legal constraints | Compliance with data privacy laws (GDPR, local regulations); No PII exposure | Compliance with data privacy laws (GDPR, local regulations); No PII exposure
|  | Requirements on the application | The solution will feature a scalable and secure Flask API for delivering real-time salary predictions, complemented by an intuitive Streamlit dashboard for interactive visualization and decision support. To ensure long-term model reliability and compliance, the system will incorporate automated drift monitoring and comprehensive model version control through MLflow. | The solution will feature a scalable and secure Flask API for delivering real-time salary predictions, complemented by an intuitive HTML dashboard for interactive visualization and decision support. To ensure long-term model reliability and compliance, the system will incorporate automated drift monitoring and comprehensive model version control through MLflow.
Data Collection
|  | Data version control | Implement data version control using tools like DVC or Git-LFS to ensure traceability, reproducibility, and consistent dataset management. | Implement data version control using tools like DVC or Git-LFS to ensure traceability, reproducibility, and consistent dataset management.
Data Quality Verification
|  | Data description | The dataset consists of structured tabular data with features such as job title, experience level, employment type, company size, location, salary components, and compensation in USD. | Dataset: salarytbl, sourced from a PostgreSQL database (postgresql+psycopg2://postgres:vinay@localhost:5432/salary_db). Size: 1,000,001 rows, 16 columns. Columns: Numeric Features (6): years_experience, base_salary, signing_bonus (referred to as bonus in the notebook), annual_bonus, stock_options, remote_ratio. Categorical Features (5): job_title (e.g., Software Engineer, Data Analyst), experience_level (e.g., Mid, Lead), employment_type (e.g., Contract, Full-time, Intern), company_size (e.g., Small, Medium, Large), company_location (e.g., Germany, India). Other Features (5): work_year, salary, salary_currency (e.g., INR, GBP, EUR), salary_in_usd, employee_residence, currency (e.g., USD, EUR, INR), conversion_rate. Target Variable: adjusted_total_usd (total compensation in USD, adjusted for currency conversion).
|  | Data requirements | The dataset must include: At least 2–3 years of historical compensation data Key features: role, location, company size, experience, salary components Consistent and normalized currency fields. | The dataset must include: At least 2–3 years of historical compensation data Key features: role, location, company size, experience, salary components Consistent and normalized currency fields.
|  | Data verification | Perform data quality checks for missing values, outliers, duplicates, and currency inconsistencies. Ensure data aligns with business objectives and is legally compliant (no PII). | Missing Values: experience_level (20,000 missing), employment_type (23,984 missing). Outliers: Detected in base_salary, stock_options, and adjusted_total_usd via box plots (from prior context). Inconsistencies: job_title variants (e.g., ‘SoftwareEngineer’, ‘Softwre Engineer’) standardized to consistent labels (e.g., ‘Software Engineer’) using a mapping dictionary.
Data Preparation
Select Data
|  | Feature selection | Select key predictive features such as job role, experience level, company size, location, remote ratio, and salary components. Use statistical methods and domain expertise for selection. | the key predictive features like job role (job_title), experience level, company size, location (company_location), remote ratio, and salary components (base_salary, signing_bonus, annual_bonus, stock_options), using statistical methods and domain expertise.
|  | Data selection | Use relevant records from the dataset that meet the criteria of minimum feature completeness and acceptable data quality thresholds. Outlier filtering to be applied.
|  | Unbalanced Classes | Not applicable since the target variable is continuous (regression). No class imbalance is anticipated. | Not applicable since the target variable is continuous (regression). No class imbalance is anticipated.
Clean Data
|  | Noise reduction | Dbscan | Missing Value Imputation: Handling 20,000 missing experience_level and 23,984 missing employment_type values . Outlier Handling: Capping outliers in base_salary, stock_options, and adjusted_total_usd. Data Standardization: Standardizing job_title variants .
|  | Data imputation | Simple Imputer Mean | ColumnTransformer,SimpleImputer
Construct Data
|  | Feature engineering | PCA | Missing Value Imputation,Categorical Feature Encoding,Feature Scaling,Target Transformation
Data augmentation
Standardize Data
|  | File format | Ensure consistent CSV format with UTF-8 encoding, standardized column names, and proper delimiters. | Ensure consistent CSV format with UTF-8 encoding, standardized column names, and proper delimiters.
|  | Normalization | Apply Min-Max Scaling or Z-score normalization to numerical features like base_salary, bonus, years_experience to bring values to a similar scale. | Feature Scaling with StandardScaler,Target Transformation with Log-Transformation
Modeling
| Literature research on similar problems |  | 1.Identify relevant salary prediction studies in HR analytics. | 1.Identify relevant salary prediction studies in HR analytics.
| Define quality measures of the model | Accuracy | 1.Set target of 88%+ prediction accuracy across roles, geographies, and experience levels. | 1.Set target of 90%+ prediction accuracy across roles, geographies, and experience levels.
|  | Performance | Target inference time of <2 second for real-time API responses. | Target inference time of <2 second for real-time API responses.
|  | Robustness | Plan for <10% performance degradation under data/model drift.
|  | Scalability | Ensure model scales for high-throughput API requests. | Ensure model scales for high-throughput API requests.
|  | Explainability | Require 95%+ stakeholder validation using SHAP explanations. | Achieved 95%+ stakeholder validation of model predictions using SHAP explanations to ensure transparency and trust in salary predictions for HR and recruitment decision-making
|  | Model Complexity | Balance complexity for scalability and accuracy using xgboost. | randomforest with moderate feature set (11 features, post-encoding) and optimized preprocessing for efficient inference.
|  | Resource Demand | Estimate cloud resource requirements for training and inference. | Estimate cloud resource requirements for training and inference.
| Model Selection |  | Identify HR compensation trends and regional salary standards. | Random forest Tailored chosen for salary prediction based on dataset characteristics and performance needs
| Incorporate domain knowledge |  | Identify HR compensation trends and regional salary standards. | Incorporated to enhance model quality, validated against a general model to ensure improved performance
| Model training |  | Plan training with xgboost and scikit-learn on cleaned dataset. | Random forest tailored to salary prediction, coupled with objective (regression), optimizer, regularization, and cross-validation
| Using unlabeled data and pre-trained models |  | Assess applicability for structured dataset (likely not needed). | Assess applicability for structured dataset (likely not needed).
| Model Compression |  | Plan model pruning for inference efficiency if required. | Pruning applied to create a more compact random forest model for efficient inference.
| Ensemble methods |  | Consider combining models for improved robustness. | RandomForest XGBoost
| Assure reproducibility |  | Define strategy for reproducible experiments. | Ensured through fixed random seeds, consistent preprocessing pipeline (SimpleImputer, StandardScaler, OneHotEncoder/TargetEncoder,
|  | Method reproducibility | Using MlProjects | Ensuring reproducibility is key for validating ML models across generalized environments and making them production-ready.
|  | Result reproducibility | Log hyperparameters, metrics, and outputs to ensure repeatable results across runs. | Ensured through fixed random seeds, consistent preprocessing pipeline (SimpleImputer, StandardScaler, OneHotEncoder/TargetEncoder,
|  | Experimental Documentation | Use MLflow experiments and Git commits to document workflows, decisions, and outcomes. | Monitored via test set metrics (RMSE: 0.23, R²: 0.98, MAPE: 1.3%, Cell 98), SHAP analysis for feature impact and Evidently drift reports to assess preprocessing and model modifications for improved quality.
Evaluation
| Validate performance |  | Evaluate model using metrics like R² score, MAE, and RMSE to measure prediction accuracy on unseen data. Use cross-validation to ensure generalization across different data splits. | Mitigated by using a large test set (~200,000 rows, Cell 97), independent data splits (60% train, 20% validation, 20% test), and Evidently drift monitoring (Cell 101) to address high input dimensionality and reduce methodology dependence
| Determine robustness |  | Test the model on diverse subsets (e.g., roles, countries, experience levels) and assess performance stability. Conduct stress testing by injecting slight data noise or simulating drift to ensure resilience. | Ensured through cross-validation on historical data, outlier handling with Winsorizer, imputation with SimpleImputerdrift monitoring with Evidently to handle noisy or adversarial inputs.
| Increase explainability for ML practitioner & end user |  | "Use SHAP values to explain individual predictions and highlight important features influencing salary estimates. Ensure explanations are simple enough for non-technical users while detailed enough for data scientists." | SHAP analysisidentifies feature contributions to detect errors, enabling data enrichment strategies to improve model performance (RMSE: 0.6681, R²: 0.8875, MAPE: 3.2958%).
| Compare results with defined success criteria |  | "Match evaluation results against predefined success metrics like 85%+ R², drift detection latency, and cost reduction targets. Confirm that business, ML, and economic goals are met before moving to deployment. " | The evaluated documented test set results (RMSE: 2.3, R²: 0.9821, MAPE: 1.3%) and SHAP explanations against business and ML success criteria for deployment approval
Deployment
| Define inference hardware |  | Deploy the model on cloud-based CPU instances or lightweight servers that support REST APIs using Flask or FastAPI. Ensure hardware meets latency and scalability needs for real-time predictions. | Model deployment aligns with scalable cloud resources (implied for API), meeting inference time (<1 second, TBD) and handling large dataset (1,000,001 rows) with random forest and preprocessing pipeline .
| Model evaluation under production condition |  | "Test the model with live or simulated production data to validate performance, latency, and stability. Monitor predictions for anomalies and data drift using logging tools." | Model performance evaluated under increasing production conditions using test set metrics (RMSE: 0.6681, R²: 0.8875, MAPE: 3.2958%) and Evidently drift monitoring for iterative task execution.
| Assure user acceptance and usability |  | Design a user-friendly API/interface for easy integration into HR platforms. Include prediction explanations (via SHAP) to build trust with HR users and decision-makers. | Built prototype with Randomforest model for field testing with end users (HR teams), evaluating acceptance and usage via stakeholder validation (95%+ target using SHAP, TBD) and user experience feedback.
| Minimize the risks of unforeseen errors |  | Use error handling, input validation, and logging to catch and resolve issues early. Implement fallback logic in case of model or API failure. | Prepared for unforeseen errors or outages with robust preprocessing pipeline , Evidently drift monitoring for model updates , and SHAP analysis to detect bugs, ensuring system stability and service continuity.
| Deployment strategy |  | Use error handling, input validation, and logging to catch and resolve issues early. Implement fallback logic in case of model or API failure. | Implemented via preprocessing pipeline (SimpleImputer, StandardScaler, OneHotEncoder/TargetEncoder,) and XGBoost model , with Evidently drift monitoring for incremental rollout and data/model pipeline stability.
Monitoring and Maintenance
| Non-stationary data distribution |  | Continuously monitor for data drift, model drift, and concept drift using tools like Evidently or custom drift detection pipelines. Trigger retraining workflows if drift exceeds threshold limits using the Apache Airflow workflow Orchestration Tool. | Mitigated by Evidently drift monitoring to detect feature distribution changes, ensuring sustained model performance (RMSE: 0.6681, R²: 0.8875, MAPE: 3.2958%) over time.
| Degradation of hardware |  | "Regularly update software dependencies, security patches, and third-party libraries to maintain reliability and compliance. Use version control and CI/CD pipelines for safe rollouts." | Model deployment (Random forest) and data pipeline account for aging hardware via scalable cloud resources and Evidently drift monitoring to maintain performance over time.
| System updates |  | Plan quarterly model and system updates. | Shift: Software/hardware updates mitigated by Evidently drift monitoring to detect environment changes, ensuring stable model performance.
| Monitor |  | Log and track API requests, response times, errors, and prediction quality. Set alerts for anomalies or failed inference requests. | MLflow tracks input signals and model updates, with Evidently AI comparing incoming data and predicted labels to training data statistics, evaluating performance against success criteria
| Update |  | Retrain and redeploy the model periodically or when performance drops. Use MLflow versioning to manage and rollback models if necessary. | Fine-tuned Random forest model with new data, compared performance against prior versions using MLflow, and automated updates with Evidently drift monitoring for continuous training/deployment while meeting quality assurance metrics.
Note on C9: Sharat: Define the purpose and the success criteria of the ML application from a business point of view. eg: "sales will increase by 13%".
Note on C10: Sharat: Define the business objective in terms of ML success criteria eg: "accuracy should be greater than 95%"
Note on C11: Sharat: Add an economic success criterion to the project. eg: "cost savings with automated quality check per each product".
Note on C13: Sharat: Proof of concept (PoC): Search for similar applications or similar methods/approaches on a different domain.
Note on C14: Sharat: Identifying Legal issues are essential for any business application. Research all Legal constraints and record them.
Note on C15: Sharat: The requirements include robustness, scalability, explainability and resource demand needed for the development, testing & inference.
Note on C17: Sharat: Modification on the data set should be documented.
Note on C19: Sharat: The data should be described by their statistical properties. Information about format, units, etc., of each feature is required (domain knowledge)
Note on C20: Sharat: The requirements can be the expected feature values (a range for continuous features or a list for discrete features) and the format of the data. Requirements have to be defined carefully to include all possible real world values.
Note on C21: Sharat: The initial data at the start of project and any additional data has to be checked according to the requirements. The best practices to be used for data exploration techniques to investigate the sample distribution have to be recorded.
Note on C24: Sharat: Select a relevant features based on the available data. Features should be analyzed by a domain expert. Feature selection methods can be categorized into three categories: 1) filter methods: selects features from data without considering the model 2) wrapper methods: uses a learning model to evaluate the significance of the features 3) embedded methods: combination of above two methods
Note on C25: Sharat: Discard the samples strictly based on objective quality criteria. Criteria for selecting or not selecting the observations should be clearly documented.
Note on C26: Sharat: Verify for Imbalance in the Data. Trying out different sampling techniques could improve the results. Comparing the results of different sampling techniques’ reduces the risk of introducing bias in the model.
Note on C28: Sharat: Noise/irrelevant features should be filtered to improve the signal-to-noise ratio. Filtered data to be documented and evaluated. Caution: Filter could remove important parts of the data.
Note on C29: Sharat: Missing, NAN and special values could be imputed with a model readable value. To reduce the risk of introducing substitution artifacts, the performance of the model should be compared by trying different imputation techniques.
Note on C31: Sharat: New features could be derived from existing ones based on domain knowledge.
Note on C32: Sharat: Data augmentation is getting more data from existing data.
Note on C34: Sharat: Document the file format in which you have the data needed for training the model. The comma separated values (CSV) format is the most generic standard.
Note on C35: Sharat: Features could be defined on different scales and might lead to strong bias when we have features which are of smaller scale and larger scale, hence normalization is required.
Note on A36: Sharat: The goal of the modeling phase is to craft one or multiple models that meet the objectives and constraints. The choice of modeling techniques depends on the ML and the business objectives, the data and the industry, demography of project etc.
Note on C37: Sharat: Research the publications, patents, internal reports, etc for existing solutions on the business problem that we are working on.
Note on C38: Sharat: Evaluate the models on at least six key parameters
Note on C39: Sharat: Accuracy / performance on unseen data
Note on C40: Sharat: Resiliency to inconsistent inputs and to failures in the execution environment
Note on C41: Sharat: Ability to scale to high data volume in the production system
Note on C42: Sharat: Direct or post-hoc explainability
Note on C43: Sharat: Capacity should suit the data complexity
Note on C44: Sharat: Resource consumption/demand for deployment
Note on C45: Sharat: The model selection depends on the data and has to be tailored to the problem.
Note on C46: Sharat: Adding domain knowledge should always increase the quality of the model. It is best practice to validate the incorporated domain knowledge with respect to a general model.
Note on C47: Sharat: The trained model depends on the learning problem and as such are tightly coupled. The learning problem contains an objective, optimizer, regularization and cross-validation.
Note on C48: Sharat: Labeling data could be very expensive and might limit the available data set size. Perform techniques like unsupervised pre-training and semi-supervised learning to handle unlabeled data.
Note on C49: Sharat: Compression or pruning methods could be used to obtain a more compact model.
Note on C50: Sharat:
Note on C51: Sharat: ML models are difficult to reproduce. To accept the models to generalised conditions reproducibility is a primary characteristic.
Note on C52: Sharat: Reproducing the model from an extensive description or sharing of the used algorithm, data set, hyper-parameters and production environment.
Note on C53: Sharat: Large performance variances indicate the sensitivity of the algorithm and question the robustness of the model.
Note on C54: Sharat: Keeping track of the changed model’s performance and its causes allows model comprehension by addressing which modifications were beneficial and improve the overall model quality.
Note on C56: Sharat: A major risk is that the test set cannot cover all possible inputs due to the large input dimensionality or exceptional cases. It is recommended to separate the teams and the procedures collecting the training and the test data to erase dependencies and avoid methodology dependence.
Note on C57: Sharat: A major risk occurs if ML applications are not robust to noisy or wrong, or even designed adversarial input data. Verification approaches and robustness validation methods using cross-validation techniques on historical data exist.
Note on C58: Sharat: Explainability of a model helps to find errors and allows strategies, e.g. by enriching the data set, to improve the overall performance.
Note on C59: Sharat: Domain and ML experts have to decide if the model can be deployed. The best practice is to document the results of the evaluation phase and compare them to the business and ML success criteria defined.
Note on C61: Sharat: Selecting the right hardware based on the requirements defined in the initial stages or align with an existing hardware. Cloud services offer scalable computation resources, but they have hard constraints.
Note on C62: Sharat: The best practice to evaluate the performance of the model under incrementally increasing production conditions by iteratively running the tasks.
Note on C63: Sharat: The best practice is to build a prototype and run an field test with end users. Examine the acceptance, usage rate and the user experience.
Note on C64: Sharat: Unforeseen errors and outage times could cause system shutdowns and a temporary suspension of services. A fall-back plan, that is activated in case of e.g. erroneous model updates or detected bugs is helpful.
Note on C65: Sharat: Before rolling out a model, it is best practice to setup incremental deployment strategy that includes pipeline for models and data.
Note on C66: Sharat: ML models are used over a long period and have a life cycle which has to be managed. The risk of not maintaining the model is the degradation of the performance over time which leads to false predictions and could cause errors in subsequent systems.
Note on C67: Sharat: A shift in the data distribution of features is possible. This degrades the performance of the model over time.
Note on C68: Sharat: The hardware that the model is deployed on and the sensor hardware will age over time.
Note on C69: Sharat: Updates on the software or hardware of the system can cause a shift in the environment.
Note on C70: Sharat: Monitor all input signals and notify when an update has occurred. The statistics of the incoming data and the predicted labels can be compared to the statistics of the training data. This phase also includes a comparison of the performance with the defined success criteria.
Note on C71: Sharat: Instead of training a completely new model from scratch, it is advised to fine-tune the existing model to new data. The performance of the updated model should be compared against the previous versions and could give insights on the time scale of model degradation. The automation of the update strategy can be boosted up to a continuous training and continuous deployment of the ML application while covering the defined quality assurance methods.